## Committee Scope
# | Scope Area | Description | Objective
1 | Physical Verification & Valuation | Conducting a thorough count, technical classification, and financial evaluation of all materials and assets. | Accurate physical count of all inventory
2 | Audit Point Closure | Systematically addressing and closing all outstanding findings from previous internal audits. | 100% closure of audit findings
3 | Asset Optimization & Cost Reduction | Strategically identifying usable materials for internal reallocation to projects, minimizing procurement costs. | SAR 500K+ in reallocated materials
4 | Scrap Management | Classifying and appraising all non-usable materials designated as scrap for profitable disposal. | Maximize value from scrap sales

## Timeline Overview
Day | Date | Phase | Region | Location | Type | Storekeeper | Activities
Mon | Dec 1 | Phase 1: Preparation | - | Kick-off Meeting | - | All Members | Assign tasks, review plan, define inventory objectives
Tue | Dec 2 | Phase 1: Preparation | - | Review Audit Findings | - | Committee Lead | Compile and distribute previous audit findings
Wed | Dec 3 | Phase 1: Preparation | - | Review Audit Findings | - | Committee Lead | Continue audit review
Thu | Dec 4 | Phase 1: Preparation | - | Prepare Documentation | - | Logistics Dept | Prepare stock lists and inventory count tags
Fri | Dec 5 | WEEKEND | - | - | - | - | Weekend
Sat | Dec 6 | Phase 1: Preparation | - | Define Inventory Scope | - | Committee Lead | Identify warehouses and areas, assign teams
Sun | Dec 7 | Phase 1: Preparation | - | Final Preparation | - | All Members | Equipment & documents ready
Mon | Dec 8 | Phase 2: Field Execution | CENTRAL | Riyadh Main Warehouse | Warehouse | Ali Mohammad Arif | Physical count, technical inspection
Tue | Dec 9 | Phase 2: Field Execution | CENTRAL | Diriyah 8242 Project | Project | Ahmed Gaffar | Physical count, close audit findings
Wed | Dec 10 | Phase 2: Field Execution | CENTRAL | RUMAH 380KV BSP | Project | Mahmoud Abouelmagd | Physical count, scrap segregation
Thu | Dec 11 | Phase 2: Field Execution | CENTRAL | Buffer Day | - | - | Complete Central region
Fri | Dec 12 | WEEKEND | - | - | - | - | Weekend
Sat | Dec 13 | Phase 2: Field Execution | EASTERN | Dammam Warehouse | Warehouse | Mohammad Tahir | Physical count, technical inspection
Sun | Dec 14 | Phase 2: Field Execution | EASTERN | Hafar Al-Batin WH + Modon | WH+Proj | Ahmed Elshenawy | Physical count, close audit findings
Mon | Dec 15 | Phase 2: Field Execution | EASTERN | Jafurah 380/230kV BSP | Project | Mohamed Elshafey | Physical count, scrap classification
Tue | Dec 16 | Phase 2: Field Execution | EASTERN | Aindar Project | Project | Mahmoud Soltan | Physical count, QC assessment
Wed | Dec 17 | Phase 2: Field Execution | WESTERN | Jeddah + Asfan WH | Warehouse | Amr Elkholy | Physical count, technical inspection
Thu | Dec 18 | Phase 2: Field Execution | WESTERN | Makkah + Madinah WH | Warehouse | Abdelazim | Physical count, close audit findings
Fri | Dec 19 | WEEKEND | - | - | - | - | Weekend
Sat | Dec 20 | Phase 2: Field Execution | NORTHERN | Tabuk ISP + OSP WH | Warehouse | Nazir Ali | Physical count, technical inspection
Sun | Dec 21 | Phase 2: Field Execution | NORTHERN | NEOM PSSA/PSSB + EV2 | Project | Mahmoud + Team | Physical count, scrap segregation
Mon | Dec 22 | Phase 2: Field Execution | SOUTHERN | Jizan Warehouse | Warehouse | Quirino Sevilla | Physical count, technical inspection
Tue | Dec 23 | Phase 2: Field Execution | SOUTHERN | Farasan + Modon Asir | Project | Mahmoud + Nawaf | Physical count, close audit findings
Wed | Dec 24 | Phase 3: Data Entry | - | Data Entry | - | All Team | Enter physical count into ERP
Thu | Dec 25 | Phase 3: Data Entry | - | Data Entry Continued | - | All Team | Continue ERP data entry
Fri | Dec 26 | WEEKEND | - | - | - | - | Weekend
Sat | Dec 27 | Phase 3: Data Entry | - | Variance Analysis | - | Finance + Logistics | Compare physical vs system
Sun | Dec 28 | Phase 3: Data Entry | - | Investigate Variances | - | Committee | Investigate causes & recommendations
Mon | Dec 29 | Phase 4: Final Report | - | Prepare Final Report | - | Committee Lead | Compile results, variances, conditions
Tue | Dec 30 | Phase 4: Final Report | - | Finalize Report | - | Committee Lead | Scrap report, audit closure
Wed | Dec 31 | Phase 4: Final Report | - | Submit to Management | - | Committee Lead | Senior management approval

## Storekeepers by Location
# | Location | Storekeeper Name | Code | Region | Type
1 | Riyadh Warehouse | Ali Mohammad Arif | 141 | Central | Warehouse
2 | Diriyah 8242 | Ahmed Gaffar Soliman | 2808 | Central | Project
3 | RUMAH BSP | Mahmoud Abouelmagd | 275 | Central | Project
4 | Dammam Warehouse | Mohammad Tahir + Hussain Alqrtas | 201 | Eastern | Warehouse
5 | Jafurah BSP | Mohamed Naser Elshafey | 2720 | Eastern | Project
6 | Aindar Project | Mahmoud Mohamed Soltan | 2806 | Eastern | Project
7 | Hafar Al-Batin | Ahmed Elshenawy | 2699 | Eastern | Project
8 | Asfan Warehouse | Amr Elkholy (Supervisor) | 3396 | Western | Warehouse
9 | Madinah Warehouse | Abdelazim Mohamed | 2817 | Western | Warehouse
10 | Waly Alahad-3 | Abdulaziz Asiri | 2196 | Western | Project
11 | Buhaiyrat | Abdullah Alshehri | 1972 | Western | Project
12 | Tabuk ISP | Nazir Ali Dhastaheer | 124 | Northern | Warehouse
13 | NEOM PSSA/PSSB | Mahmoud Abdelshafy | 2695 | Northern | Project
14 | NEOM EV2 | Augusto + Ahmed Hatab | 1118 | Northern | Project
15 | Jizan Warehouse | Quirino JR Sevilla | 387 | Southern | Warehouse
16 | Farasan Island | Mahmoud Sabry Ahmed | 2975 | Southern | Project
17 | Modon Asir | Nawaf Ibrahim Asiri | 2197 | Southern | Project

## KPIs Tracking
Category | KPI Name | Formula / Description | Target | W1 | W2 | W3 | W4 | Final
Accuracy & Efficiency | Inventory Record Accuracy (IRA) | (Matching items / Total items) × 100 | > 98%
Accuracy & Efficiency | Plan Completion Rate (PCR) | (Tasks on time / Total tasks) × 100 | 100%
Compliance & Closure | Internal Audit Findings Closure (IAFCR) | (Findings closed / Total findings) × 100 | 100%
Financial Value | Value of Reallocated Materials (VRM) | Total value transferred to projects | SAR 500K+
Financial Value | Value of Recovered Scrap (VRS) | Total value of scrap ready for sale | TBD
Financial Value | Slow-Moving & Obsolete Stock (SLOB) | Total value not used over 12 months | Identify

## Committee Members
Role | Department | Responsibilities
Committee Lead | Operations | Overall supervision, ensuring adherence to timeline, resolving disputes.
Engineering Representative | Engineering | Technical evaluation of equipment, assets, and specialized materials.
Quality Control (QC) Representative | Quality Control | Inspecting material quality and ensuring it meets specifications.
Logistics Management Representative | Supply Chain | Coordinating inventory counts and providing stock records.
Finance Representative | Finance | Financial valuation of materials and recording results in financial system.