# Material Inventory & Technical Committee (MITC)

Action Plan - Annual Inventory 2025

Nesma Infrastructure & Technology

December 1 - 31, 2025

Executive Summary • Total Main Warehouses: 5 locations across 5 regions and project Warehouse ??? • Total Project Sites/Store with Storage: 15+ locations with dedicated storekeepers • Total Items to Count: 800,000+ material items • Approach: Central Warehouses FIRST → Then Project Sites in same region

# 1. Preamble & Strategic Objectives

In line with Nesma Infrastructure's commitment to operational excellence and asset optimization, the Material Inventory & Technical Committee (MITC) is mandated to conduct the comprehensive annual inventory for the year 2025. This critical initiative will be executed from December 1, 2025, to December 31, 2025, encompassing all central and project warehouses.

The primary objectives of this mandate are not only to achieve an accurate physical count but also to drive significant value for the organization.

# 2. Committee's Scope of Work

| # | Scope Area | Description |
| --- | --- | --- |
| 1 | Physical Verification & Valuation | Conducting a thorough count, technical classification, and financial evaluation of all materials and assets. |
| 2 | Audit Point Closure | Systematically addressing and closing all outstanding findings from previous internal audits to ensure full compliance and process integrity. |
| 3 | Asset Optimization & Cost Reduction | Strategically identifying and evaluating usable materials for internal reallocation and transfer to projects, thereby minimizing new procurement costs and maximizing the utilization of existing assets. |
| 4 | Scrap Management | Classifying and appraising all non-usable materials designated as scrap, preparing them for efficient and profitable disposal. |

# 3. Committee Members and Responsibilities

The committee consists of representatives from the following departments to ensure a comprehensive inspection and evaluation:

| Role | Department | Responsibilities |
| --- | --- | --- |
| Committee Lead | Supply Chain | Overall supervision, ensuring adherence to the timeline, and resolving any disputes. |
| Project Representative | Operations | Overall supervision, ensuring |
| Engineering Representative | Engineering | Technical evaluation of equipment, assets, and specialized materials. |
| QC Representative | Quality Control | Inspecting material quality and ensuring it meets specifications. |
| Logistics Management Representative | Supply Chain | Coordinating inventory counts within warehouses and providing stock records. |
| Finance Representative | Finance | Financial valuation of materials and overseeing the recording of results in the financial system. |

## 3.1 Local Support - Storekeepers by Location

| Location | Storekeeper | Region | Type |
| --- | --- | --- | --- |
| Riyadh Warehouse | Ali Mohammad Arif | Central 2 days | Warehouse |
| Diriyah 8242 x2 | Ahmed Gaffar Soliman | Central 1 day | Project Store |
| Dammam Warehouse | Mohammad Tahir + Hussain Alqrtas | Eastern 2 days | Warehouse |
| Jafurah BSP | Mohamed Naser Elshafey | Eastern 1 day | Project Store |
| Aindar Project | Mahmoud Mohamed Soltan | Eastern 1 day | Project Store |
| Hafar Al-Batin | Ahmed Elshenawy | Eastern 1 day | Project Store |
| Ras tanora | amir | Eastern 1 day | Project Store |
| Asfan Warehouse | Amr Elkholy (Supervisor) | Western 2 days | Warehouse |
| Madinah Warehouse | Abdelazim Mohamed | Western1 day | Warehouse |
| Aramco Jed NJBP | Mahmod albanaa | Western1 day | Project Store |
| Aramco yanbue | yasin | Western1 day | Project Store |
| Buhaiyrat | Abdullah Hassan Saleh Alshehri | Western1 day | Project Store |
| Tabuk ISP | Nazir Ali Dhastaheer | Northern all 1-2 days | Warehouse |
| NEOM PSSA/PSSB | Mahmoud Abdelshafy | Northern | Project Store |
| NEOM EV2 | Augusto + Ahmed Hatab | Northern | Project Store |
| Jizan Warehouse | Quirino JR Sevilla | Southern 1 day | Warehouse |
| Farasan Island | Mahmoud Sabry Ahmed | Southern 1 day | Project Store |
| Modon Asir - abha | Nawaf Ibrahim Asiri/mahjob | Southern 1 day | Project Store |

# 4. Detailed Timeline & Phases

## Phase 1: Preparation and Planning (Dec 1-7, 2025)

| Date | Activity | Responsible |
| --- | --- | --- |
| Dec 1 | Kick-off Meeting: Assign tasks, review plan, define inventory objectives | All Committee Members |
| Dec 2-3 | Review Internal Audit Findings: Compile and distribute all previous audit findings | Committee Lead |
| Dec 4-5 | Prepare Documentation: Current stock lists and inventory count tags | Logistics Department |
| Dec 6-7 | Define Inventory Scope: Identify warehouses and areas, assign teams | Committee Lead |

## Phase 2: Field Execution (Dec 8-21, 2025)

Central Warehouses FIRST → Then Project Sites

### Field Activities:

- Physical Count: Teams begin the physical counting of materials in central and project warehouses.

- Technical Inspection & Quality Assessment: Engineering and QC representatives inspect materials and classify their condition (new, used, damaged, scrap).

- Close Audit Findings: Teams verify and address previous findings on-site, documenting corrective actions taken.

- Scrap Segregation & Classification: All items classified as 'scrap' are collected in a designated area. Technical team evaluates and categorizes them (metals, cables, wood) for sale.

### Field Visit Schedule:

| Date | Region | Location | Type | Storekeeper |
| --- | --- | --- | --- | --- |
| Dec 8 | CENTRAL | Riyadh Main Warehouse | Warehouse | Ali Mohammad |
| Dec 9-10 | CENTRAL | Diriyah 8242 + RUMAH BSP Projects | Project | Ahmed + Mahmoud |
| Dec 12-13 | EASTERN | Dammam + Hafar Al-Batin Warehouses | Warehouse | Mohammad Tahir |
| Dec 14-15 | EASTERN | Jafurah BSP + Aindar Projects | Project | Mohamed + Mahmoud |
| Dec 16-17 | WESTERN | Jeddah + Asfan Warehouses | Warehouse | Amr Elkholy |
| Dec 18 | WESTERN | Makkah + Madinah Warehouses | Warehouse | Abdelazim |
| Dec 19 | NORTHERN | Tabuk ISP + OSP Warehouses | Warehouse | Nazir Ali |
| Dec 20 | NORTHERN | NEOM PSSA/PSSB + EV2 Projects | Project | Mahmoud + Team |
| Dec 21 | SOUTHERN | Jizan WH + Farasan + Modon Asir | WH + Proj | Quirino + Team |

## Phase 3: Data Entry and Reconciliation (Dec 22-28, 2025)

- Data Entry: Results of the physical count are entered into the ERP system.

- Variance Analysis: Finance and Logistics departments compare physical count with system balances to identify variances (surplus or deficit).

- Investigate Variances: Committee meets to investigate causes of significant variances and provide recommendations.

## Phase 4: Final Report and Recommendations (Dec 29-31, 2025)

The Committee Lead prepares a comprehensive report including:

- Final inventory results and total stock value

- List of variances, their causes, and adjustments made

- Summary of material conditions (new, damaged, slow-moving)

- Separate report on materials classified as scrap with estimated value

- Confirmation that all internal audit findings have been closed

- Submit to Senior Management for approval and sign-off

# 5. Key Performance Indicators (KPIs)

Using these KPIs will transform the committee's work from a mere "operational task" into a "strategic initiative" that contributes directly to the company's financial performance.

## 5.1 Accuracy and Efficiency KPIs

| KPI Name | Formula | Target | Actual |
| --- | --- | --- | --- |
| Inventory Record Accuracy (IRA) | (Number of matching items / Total items counted) × 100 | > 98% |  |
| Plan Completion Rate (PCR) | (Tasks completed on time / Total planned tasks) × 100 | 100% |  |

## 5.2 Compliance & Closure KPIs

| KPI Name | Formula | Target | Actual |
| --- | --- | --- | --- |
| Internal Audit Findings Closure Rate (IAFCR) | (Number of findings closed / Total targeted findings) × 100 | 100% |  |

## 5.3 Financial Value & Cost Reduction KPIs

These are the most critical indicators, demonstrating the direct financial return of the committee's activities.

| KPI Name | Description | Target | Actual |
| --- | --- | --- | --- |
| Value of Reallocated Materials (VRM) | Total value of materials identified as "usable" and successfully transferred to projects (direct cost savings) | SAR 500K+ |  |
| Value of Recovered Scrap (VRS) | Total estimated value of materials classified as "scrap" and ready for sale | TBD |  |
| Value of Slow-Moving & Obsolete Stock (SLOB) | Total value of materials not used over 12 months (identify capital tied up in non-moving inventory) | Identify & Report |  |

## 5.4 How to Use These KPIs

- Before Starting: Committee must agree on these KPIs and set specific targets for each.

- During the Process: KPIs should be tracked periodically (weekly) to monitor progress.

- In the Final Report: Must include a dedicated section showcasing actual results for each KPI against its target.

# 6. Approvals

| Prepared By: _________________________ Date: ____/____/2025 | Reviewed By: _________________________ Date: ____/____/2025 | Approved By: _________________________ Date: ____/____/2025 |
| --- | --- | --- |