Report on the Visit to the Central Region

Based on the inventory committee's visit to the projects and warehouses in the Central Region, the following points were identified:

First: Tuwaiq Warehouses

1. Inventory is 100% complete.

2. There is a large quantity of scrap materials (cables and metals) occupying a significant area.

3. The existing locks are small in size and not secure.

4. The main doors require maintenance.

5. There are numerous boxes of materials belonging to the Airport project, which has been closed for a long time.

Second: Al-Marjan Site

Many of the materials present on the project are not needed, and there is no confirmation from the project management regarding surplus materials—whether those still on the project or those stored in Tuwaiq warehouses.

Third: Ramah Project

1. The storage area is not proportionate to the volume of materials that will be supplied to the project.

2. The closed warehouse is not secure, as it can easily be broken into due to the low height of the surrounding fence, in addition to the absence of cameras.

3. The expansion plans sent by the Logistics Department were rejected by PM/SM, noting that next month at least 800 drums of cables will be supplied.

4. GIS equipment has been received and is fully stored on-site, exposing the accessories to the risk of damage due to heavy rainfall in the area or theft.

Fourth: KSP Project

1. There is no warehouse keeper, and consequently no inventory has been conducted for 12 drums of control cables, in addition to a container full of materials with no control over material movement.

2. Security is not present permanently, and there is another door inside the warehouse that is not secured.

3. There is no clear visibility of unfinished works or surplus materials that could be used in the company's other projects.

Fifth: Diriyah Project

The issue of transformer transfer has been resolved, and a work strategy and follow-up plan have been established with the site managers to address any challenges, particularly those related to subcontractors.

Key Performance Indicators (KPIs) Proposed Based on the Central Region Visit Report.

Based on the key findings from the visit report (such as inventory completion, scrap materials, security, storage capacity, surplus identification, and subcontractor management), here is a set of proposed Key Performance Indicators (KPIs) to measure and improve performance in warehouse management, materials handling, and projects.

These are inspired by best practices in inventory and logistics management for engineering and construction projects.

I have categorized them according to the main themes in the report, including a definition for each KPI, calculation method, and suggested target (adjustable based on company needs).

1. Inventory Management

- Inventory Completion Rate

Definition: Measures the extent of completion of periodic inventory counts.

Calculation: (Number of inventoried items / Total number of items) × 100

Target: 100% monthly.

Relevance: Monitoring Tuwaiq warehouses and KSP project.

- Inventory Accuracy

Definition: Matching of records with actual physical stock.

Calculation: (Number of matching items / Total inventoried items) × 100

Target: >99%.

Relevance: Lack of inventory in KSP.

- Inventory Turnover Ratio

Definition: Speed of material usage or movement.

Calculation: Cost of materials used / Average inventory value

Target: >4 times annually (lower for inactive materials).

Relevance: Closed Airport project materials and unneeded items in Al-Marjan.

2. Surplus & Scrap Management

- Surplus/Scrap Rate

Definition: Percentage of space or value occupied by unused materials.

Calculation: (Value or volume of scrap/surplus / Total inventory value or volume) × 100

Target: <10%.

Relevance: Scrap cables and metals in Tuwaiq, Airport materials.

- Surplus Identification & Redistribution Rate

Definition: Speed of identifying surplus materials and reallocating them to other projects.

Calculation: (Number of identified and redistributed surplus items / Total surplus items) × 100

Target: 80% within 3 months.

Relevance: No confirmation of surplus in Al-Marjan and Ramah.

3. Storage Capacity Utilization

- Storage Utilization Rate

Definition: Efficiency of available space usage.

Calculation: (Used space / Total available space) × 100

Target: 80-90% (to avoid overcrowding or shortages).

Relevance: Insufficient space in Ramah, scrap occupying large areas.

- Expansion Plan Approval Rate

Definition: Speed of approving capacity improvement plans.

Calculation: (Number of approved plans / Total submitted plans) × 100

Target: 100% within one month.

Relevance: Rejection of expansion plans in Ramah.

4. Security & Safety

- Security Coverage Rate

Definition: Presence of guards and security systems.

Calculation: (Security presence hours / Total required hours) × 100

Target: 100% permanent presence, with cameras in 100% of sites.

Relevance: No permanent security in KSP, easy break-in in Ramah.

- Storage Safety Index

Definition: Quality of locks, doors, and fences.

Calculation: (Number of secure elements / Total elements) × 100

Target: 100%.

Relevance: Small locks, doors needing maintenance, low fence.

- Theft/Loss Incident Rate

Definition: Number of security incidents.

Calculation: Number of incidents / Number of months

Target: 0 incidents.

5. Sensitive Materials & Supply Management

- Protected Storage Rate for Sensitive Items

Definition: Safe storage of equipment away from risks (e.g., rain or theft).

Calculation: (Number of sensitive items stored safely / Total sensitive items) × 100

Target: 100%.

Relevance: GIS exposed to damage in Ramah.

- Warehouse Keeper Presence Rate

Definition: Availability of a dedicated warehouse keeper.

Calculation: (Days of presence / Total days) × 100

Target: 100%.

Relevance: No keeper in KSP.

6. Subcontractor Management

- Subcontractor Issue Resolution Rate

Definition: Speed of resolving subcontractor-related challenges.

Calculation: (Number of resolved issues / Total issues) × 100

Target: 90% within two weeks.

Relevance: Resolution of transformer transfer issue in Diriyah.

The Project Managers must direct the Project Engineers and Site Managers to conduct a quick survey of the volume of works that are still under installation, and to send detailed reports on the surplus materials as soon as possible.