### English Translation: Eastern Region Visit Report

Based on the inventory committee's visit to the projects and warehouses in the Eastern Region, the following findings were identified:

First: Main Dammam Warehouse

- Inventory completed at 100%.

- There is scrap material from cables and metals occupying a large storage area.

- There is a fault in one of the closed warehouse doors, which cannot be closed, increasing the risk level.

- Many materials returned from projects without confirmation of need or classification as surplus.

Second: Substation Projects After visiting the stations in the Eastern Region, the following was observed:

- Many materials are placed poorly without any organization.

- There is no clear plan with site managers regarding the volume of unfinished work and their need for materials in the project.

- Security in some projects is undisciplined, as we entered the project without any data registration.

- In most projects, project engineers were found in offices, while the subcontractor works without any supervision, freely disposing of materials as they wish.

- Through reviewing the scrap in the Dammam warehouse, in addition to installation works, it became clear to us that there is unreasonable waste in the used cables.

- There is no inventory of materials present in the project, and no storage spaces.

- There is a constant complaint about unclear contracts with the subcontractor, which do not hold them responsible for completing all works, causing delays in execution.

- Based on information from project engineers, there are many surplus materials, in addition to shortages in some other materials for which purchase orders have already been issued but have not arrived yet.

- The main warehouse cannot accommodate the volume of materials to be returned from projects at present.

Third: Regarding the Jafurah Project

- As is the case, there is no clear plan for the remaining work volume.

- There are many surplus materials that must be returned to the Dammam warehouse (noting the lack of sufficient space to receive all these materials).

- The inventory status at the warehouse has been verified, and a survey must be conducted on the remaining works and reuse of materials in other projects.

Fourth: Ras Tanura Warehouse

- The warehouse is not finally paved, as the soil is sandy, and with rain, the situation has become extremely bad.

- All pipes are in poor condition, filled with rust.

Proposed Key Performance Indicators (KPIs) - Vertical Format

Based on the Eastern Region Visit Report, here is the suggested set of KPIs presented vertically for easier reading (one KPI per section):

1. KPI: Inventory Accuracy

- Category: Inventory Management

- Description: Percentage of physical inventory matching records.

- Calculation Method: (Number of matching items / Total items inventoried) × 100

- Suggested Target: > 95%

- Related Issue from Report: Lack of inventory on projects, returned materials without classification

2. KPI: Inventory Turnover

- Category: Inventory Management

- Description: How often inventory is used or sold in a period.

- Calculation Method: Cost of materials used / Average inventory value

- Suggested Target: > 4-6 times per year

- Related Issue from Report: Surplus materials and shortages, limited warehouse capacity

3. KPI: Material Waste Rate

- Category: Waste & Scrap

- Description: Percentage of materials wasted or scrapped vs. used.

- Calculation Method: (Value/quantity of wasted materials / Total materials used) × 100

- Suggested Target: < 5%

- Related Issue from Report: Large scrap in warehouse, unreasonable cable waste

4. KPI: Scrap Reuse Rate

- Category: Waste & Scrap

- Description: Percentage of scrap reused or sold.

- Calculation Method: (Quantity of reused scrap / Total scrap) × 100

- Suggested Target: > 50%

- Related Issue from Report: Scrap from cables/metals occupying large space

5. KPI: Site Organization Compliance

- Category: Site Organization & Storage

- Description: Percentage of sites following organization and storage standards.

- Calculation Method: (Number of compliant sites / Total inspected sites) × 100

- Suggested Target: 100%

- Related Issue from Report: Materials placed poorly, no storage spaces

6. KPI: Supervision Coverage Rate

- Category: Supervision & Control

- Description: Percentage of time/days engineers supervise subcontractors on site.

- Calculation Method: (Actual supervision hours / Required work hours) × 100

- Suggested Target: > 80%

- Related Issue from Report: Engineers in offices, subcontractors handling materials freely

7. KPI: Site Security Compliance

- Category: Security & Safety

- Description: Percentage of entries/visits recorded per procedures.

- Calculation Method: (Correctly recorded entries / Total entries) × 100

- Suggested Target: 100%

- Related Issue from Report: Entry without registration, undisciplined security

8. KPI: Remaining Work Planning Rate

- Category: Planning & Contracts

- Description: Percentage of projects with clear plans for remaining work and material needs.

- Calculation Method: (Projects with clear plans / Total projects) × 100

- Suggested Target: 100%

- Related Issue from Report: No clear plan, complaints about unclear subcontractor contracts

9. KPI: Facility Maintenance Compliance

- Category: Facility Maintenance

- Description: Percentage of identified issues corrected within timeframe (e.g., doors, paving).

- Calculation Method: (Corrected issues / Total identified issues) × 100

- Suggested Target: > 90% within one month

- Related Issue from Report: Faulty warehouse door, unpaved sandy ground

10. KPI: Warehouse Utilization Rate

- Category: Storage Capacity

- Description: Percentage of available space used.

- Calculation Method: (Used space / Total available space) × 100

- Suggested Target: 70-85% (to allow returns)

- Related Issue from Report: Main warehouse cannot accommodate returned materials